## Work flow
Member / Epic Status | ToDo | In progress | Done
PM
PL
Developers
Assign epics
Waiting for start
Implement code
Unit Test
QA primary reception
QA secondary reception
check
Code Review
Complete
Change the status of the "Implementation" task to "In Progress" when you start the implementation work.
Create a development branch from the "Develop" branch
If a QA occurs, add a new issue to JIRA with the type "QA" and assign the person in charge to Mr. Miura.
When you receive it, set the status to "In Progress"
Answers will be reassigned to the questioner.
After confirming the answer, please set the status to "Done"
When the implementation is finished, set the status of the "Implementation" task to "Done" and the status of "Unit Test" to "In Progress". Also, please make Miyahara the person in charge of "code review".
Issue a pull request to merge your development branch into the "develop" branch.
After passing all the unit tests, set the status of "Unit test" to "Done".
Receive a pull request and do a code review.
Add subtasks if corrections are found in the code review
Confirm that the problem in the code review has been fixed and all the unit tests have passed, and approve the pull request.

## 作業フロー
Member / Status | 作業前 | 進行中 | レビュー待ち | 完了
PM
PL
Developers
エピックをアサイン
開始待ち
実装
単体テスト
QA一次受け
QA二次受け
回答チェック
レビュー
作業完了
実装作業を開始する時に「実装」のタスクのステータスを「進行中」に変更してください。ブランチも作る
QAが発生したらJIRAに新しくタイプ「QA」で課題を追加し、担当者を三浦さんにしてください。
受け取ったらステータスを「進行中」にします
回答されたものは質問者に再アサインされます。
回答を確認したらステータスを「完了」としてください
実装が終わったら「実装」のタスクのステータスを「完了」とし、「単体テスト」のステータスを「進行中」にします。また、「コードレビュー」の担当者を宮原にしてください。プルリクも出す。
単体テストを全てパスしたら「単体テスト」のステータスを「完了」にしてください。
コードレビューにおいて修正点が見つかった場合はサブタスクを追加します